## Feuil1
Task | Detail | Advancement | Difficulty | Problems | Estimated Total Time took
Look | Character basic movement ability | Done | Very Easy |  | > 2 hours
Move |  | Done | Very Easy |  | > 2 hours
Walk |  | Done | Very Easy |  | > 2 hours
Run |  | Done | Easy |  | > 2 hours
Crouch |  | To polish | Easy |  | > 2 hours
Peak |  | To polish | Easy |  | > 2 hours
Jump |  | To polish | Easy |  | > 2 hours
Vaulting over Object | Vault over an obstacles that has nothing behind, otherwise climb it | To Do | Medium |  | > 2 hours
Climbing (vent / wall / box) | Climb over an object to get on it | To Do | Medium |  | > 2 hours
Climbing Ladder | Climb on a ladder by going next to it | To Do | Very Hard |  | > 10 hours
Squeezing throught gaps | Squeeze throught tight gap | To Do | Medium |  | > 5 hours
Hiding Spots (Beds, Locker, etc …) | Spots to hide the player where the enemy will not see it, may be opened by the enemy if the player is spotted going into it | Research | Medium |  | > 2 hours
Shymmying / shaking in motion | Shake the camera while moving | To polish | Easy |  | > 2 hours
Look back when running | When running (only forward), press the peaking button to look back, if the character is colliding with anything, set the camera to normal position | To Do | Easy |  | > 2 hours
Camera (vision with camera, effect, zoom & switch) | Vision with camera out + add camera effect, zoom & animation | In progress | Easy |  | > 2 hours
Camera night vision (view, light & switch) | Night vision with camera (night effect + light added, animation for night vision switch) | In progress | Easy |  | > 2 hours
Battery system (reload, stockage & usage) | Camera battery system that decrease as camera is used + battery usage to charge it back | In progress | Easy |  | > 2 hours
Note with camera Filming | When filming with camera a precise object, it adds a sheet to the journal from the character own perspective | To Do | Medium |  | > 2 hours
Interaction (Picking Battery, Documents) | Allow interaction with element that disappear after the interaction | To Do | Easy |  | > 2 hours
Basic UI (Main menu, Options, Credits, Pause, etc… ) | Basic UI that exists in all games | To Do | Very Easy |  | > 5 hours
GUI | A game UI that change with the character capacity to interact with the environment | To Do | Easy |  | > 2 hours
Objectives + objective UI | A basic UI that give the player's objective with link to notes & journal | To Do | Medium |  | > 2 hours
Notes & Journal UI | Notes are element interactible in the game that give insight into the story, while the journal is with the camera | To Do | Medium |  | > 2 hours
Interactible Objects (Door, Main objectives) | Object that the player may interact with, that do not disappear when interacted with but may be broken by the enemy | To Do | Hard |  | > 2 hours
Save system (Position, Objectives, Battery, Timer recording) | System to save game progression with most important part | To Do | Medium |  | > 2 hours
Enemy movement (Roaming, Running, Chasing, Attacking etc…) | Enemy movement and how it works | To Do | Hard |  | > 2 hours
Enemy's player tracking (States, searching elements, etc… ) | Enemy changing states for when he gain different information that changes it's state | To Do | Hard |  | > 2 hours
Enemy's interaction with environment | Enemy is able to open and close door, search in hiding spots and vault over obstacles | To Do | Very Hard |  | > 5 hours
Enemy's animation | Animation that tell what the enemy is doing (Need duo animation when player character is grabbed by the enemy) | To Do | Might Need Professional Help |  | > 2 hours
Movement Animation (Walk, Run, Crouch, Peak, Jump, etc…) | Movement animation of the character that activate with the basic action | In progress | Hard |  | > 5 hours
Special Movement animation (Interaction, Camera open / close, etc...) | Animation that change with what type of object, the character is interacting with, need to be synced with the objects (and will be difficult) | Research | Might Need Professional Help |  | > 24 hours
Other Animation (Door/Locker opening/closing animation, ) |  | Research | Hard |  | > 5 hours

## BackEnd
Task | Advancement | Difficulty | Time took
Look | To Do | Very Easy | > 2 hours
Move | In progress | Easy | > 5 hours
Walk | Done | Medium | > 10 hours
Run | Bugged / To patch | Hard | > 24 hours
Crouch | Killed | Very Hard | > 2 days
Peak | To polish | Might Need Professional Help | > 1 weeks
Jump | Research |  | < 1 weeks
Vaulting over Object
Climbing (vent / wall / box)
Climbing Ladder
Squeezing throught gaps
Hiding Spots (Beds, Locker, etc …)
Shymmying / shaking in motion
Look back when running
Camera (vision with camera, effect, zoom & switch)
Camera night vision (view, light & switch)
Battery system (reload, stockage & usage)
Note with camera Filming
Interaction (Picking Battery, Documents)
Basic UI (Main menu, Options, Credits, Pause, etc… )
GUI
Objectives + objective UI
Notes & Journal UI
Interactible Objects (Door, Main objectives)
Save system (Position, Objectives, Battery, Timer recording)
Enemy movement (Roaming, Running, Chasing, Attacking etc…)
Enemy's player tracking (States, searching elements, etc… )
Enemy's interaction with environment
Enemy's animation
Movement Animation (Walk, Run, Crouch, Peak, Jump, etc…)
Special Movement animation (Interaction, Camera open / close, etc...)
Other Animation (Door/Locker opening/closing animation, )